## 31-Jul (2) (hidden)
2024-07-31
Task ID | Task Name | Planned Start Date | Planned End Date | Total Labour-Hour | Planned Budget ($) | Actual Cost Till Now ($) | Actual Progress (%)
1 | Market Research | 2024-02-01 | 2024-02-14 | 40 | 2000 | 2000 | 100%
2 | Website Design | 2024-02-15 | 2024-03-15 | 120 | 6000 | 6500 | 100%
3 | Front-end Development | 2024-03-16 | 2024-04-30 | 200 | 10000 | 11500 | 100%
4 | Back-end Development | 2024-05-01 | 2024-06-30 | 250 | 12500 | 14000 | 100%
5 | Testing and Debugging | 2024-07-01 | 2024-07-31 | 150 | 7500 | 8000 | 75%
6 | Deployment | 2024-08-01 | 2024-08-14 | 60 | 3000 | 0 | 0%
7 | Post-Launch Support | 2024-08-15 | 2024-09-30 | 100 | 5000 | 0 | 0%
8 | SEO Optimization | 2024-10-01 | 2024-11-15 | 80 | 4000 | 0 | 0%
9 | Social Media Marketing | 2024-11-16 | 2024-12-31 | 100 | 5000 | 0 | 0%
10 | User Feedback Collection | 2025-01-01 | 2025-01-31 | 70 | 3500 | 0 | 0%
|  | AC | EV | PV | EV / AC | EV - AC | EV / PV | EV - PV
Task ID | Task Name | ACWP | BCWP | BCWS | CPI | CV | SPI | SV
1 | Market Research | 2000 | 2000 | 2000 | 1 | 0 | 1 | 0
2 | Website Design | 6500 | 6000 | 6000 | 0.92308 | -500 | 1 | 0
3 | Front-end Development | 11500 | 10000 | 10000 | 0.86957 | -1500 | 1 | 0
4 | Back-end Development | 14000 | 12500 | 12500 | 0.89286 | -1500 | 1 | 0
5 | Testing and Debugging | 8000 | 5625 | 7500 | 0.70312 | -2375 | 0.75 | -1875
6 | Deployment | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Post-Launch Support | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | SEO Optimization | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Social Media Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | User Feedback Collection | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 42000 | 36125 | 38000 | 0.86012 | -5875 | 0.95066 | -1875

## 31-Jul
2024-07-31
Task ID | Task Name | Planned Start Date | Planned End Date | Total Labour-Hour | Planned Budget ($) | Actual Cost Till Now ($) | Actual Progress (%)
1 | Market Research | 2024-02-01 | 2024-02-14 | 40 | 2000 | 2000 | 100%
2 | Website Design | 2024-02-15 | 2024-03-15 | 120 | 6000 | 6500 | 100%
3 | Front-end Development | 2024-03-16 | 2024-04-30 | 200 | 10000 | 11500 | 100%
4 | Back-end Development | 2024-05-01 | 2024-06-30 | 250 | 12500 | 14000 | 100%
5 | Testing and Debugging | 2024-07-01 | 2024-07-31 | 150 | 7500 | 8000 | 75%
6 | Deployment | 2024-08-01 | 2024-08-14 | 60 | 3000 | 0 | 0%
7 | Post-Launch Support | 2024-08-15 | 2024-09-30 | 100 | 5000 | 0 | 0%
8 | SEO Optimization | 2024-10-01 | 2024-11-15 | 80 | 4000 | 0 | 0%
9 | Social Media Marketing | 2024-11-16 | 2024-12-31 | 100 | 5000 | 0 | 0%
10 | User Feedback Collection | 2025-01-01 | 2025-01-31 | 70 | 3500 | 0 | 0%
|  | AC | EV | PV | EV / AC | EV - AC | EV / PV | EV - PV
Task ID | Task Name | ACWP | BCWP | BCWS | CPI | CV | SPI | SV
1 | Market Research
2 | Website Design
3 | Front-end Development
4 | Back-end Development
5 | Testing and Debugging
6 | Deployment
7 | Post-Launch Support
8 | SEO Optimization
9 | Social Media Marketing
10 | User Feedback Collection
Total

## 31-Aug
2024-08-31
g
| Task ID | Task Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Total Man-Hour | Planned Budget ($) | Actual Cost Till Now ($) | Actual Progress (%)
| 1 | Market Research | 2024-02-01 | 2024-02-14 | 2024-02-01 | 2024-02-14 | 40 | 2000 | 2000 | 1
| 2 | Website Design | 2024-02-15 | 2024-03-15 | 2024-02-15 | 2024-03-20 | 120 | 6000 | 6500 | 1
| 3 | Front-end Development | 2024-03-16 | 2024-04-30 | 2024-03-20 | 2024-05-05 | 200 | 10000 | 11500 | 1
| 4 | Back-end Development | 2024-05-01 | 2024-06-30 | 2024-05-05 | 2024-07-10 | 250 | 12500 | 14000 | 1
| 5 | Testing and Debugging | 2024-07-01 | 2024-07-31 | 2024-07-01 | 2024-07-28 | 150 | 7500 | 8300 | 1
| 6 | Deployment | 2024-08-01 | 2024-08-14 | 2024-07-29 | 2024-08-16 | 60 | 3000 | 3200 | 1
| 7 | Post-Launch Support | 2024-08-15 | 2024-09-30 | 2024-08-17 |  | 100 | 5000 | 2500 | 0.5
| 8 | SEO Optimization | 2024-10-01 | 2024-11-15 |  |  | 80 | 4000 | 0 | 0
| 9 | Social Media Marketing | 2024-11-16 | 2024-12-31 |  |  | 100 | 5000 | 0 | 0
| 10 | User Feedback Collection | 2025-01-01 | 2025-01-31 |  |  | 70 | 3500 | 0 | 0
|  |  | AC | EV | PV | EV / AC | EV - AC | EV / PV | EV - PV
| Task ID | Task Name | ACWP | BCWP | BCWS | CPI | CV | SPI | SV
| 1 | Market Research
| 2 | Website Design
| 3 | Front-end Development
| 4 | Back-end Development
| 5 | Testing and Debugging
| 6 | Deployment
| 7 | Post-Launch Support
| 8 | SEO Optimization
| 9 | Social Media Marketing
| 10 | User Feedback Collection
Total

## Sheet2
Dashboard
KPIs
KPIs | 2024-07-31 | 2024-08-31
CPI
CV
SPI
SV
Task Status
Completed
Ongoing
Yet to start
Employee NPS
Employee NPS score | Out of 10
JUL | 8.5
AUG | 7
Cost
Total Budget | 58500
Actual cost | 48000